## Sheet1
Step.# | Application Area | Input | Priority | Responsibilities | Dev. Status | Dev. Remarks | SignOff Status | Instructor Remarks | Signoff remarks
1 | Idea Finalization | 1. Should cover one of three sub-domains of machine learning 2. Sample data available on Kaggle 3. Discussion with mentor | P1 | Aditya Rathore Mohil Gupta Yash Mishra | Closed | Point 1-- Done Point 2-- Point 3-- Remark 1 -- done Remark 2-- done Remark 3-- | Open
2 | Defining Biasness | 1. Discuss with mentor 2. Credible sources visit 3. Deriving meaning with respect to the project. | P1 | Aditya Rathore Mohil Gupta Yash Mishra | Closed | Point 1-- Done Point 2-- Point 3-- Remark 1 -- done Remark 2-- done | Open
3 | Events and Publishers Selection | 1. Events collection 2. Publishers collection 3. Discuss with mentor | P1 | POint 1 - Aditya Rathore Mohil Gupta Yash Mishra Point 2 - Aditya Rathore | Closed | Point 1-- Done Point 2-- Point 3-- Remark 1 -- done Remark 2-- done | Open
4 | Data collection | 1. Data collection | P1 | Point 1 - Aditya Rathore Mohil Gupta Yash Mishra | Open |  | Open
5 | Pre Processing | 1. Selecting pre determined methods to do sampling 2. Data Cleaning 3. Adding Features | P1 |  | Open |  | Open